## costos
Category | Resources | Descripcion | Costo(COP) | Unidad | Unidades Necesarias | SubTotal | Comentarios
Human Resources | Backend Developer | databases,scripting, and the architecture of websites | 50000 | Hora | 39 | 1950000
| IoT Enginier | hardware,designin and management | 50000 | Hora | 41 | 2050000
| Frontend Developer | GUI, databases and achitecture of websites | 40000 | Hora | 37 | 1480000
| Proyect Manager (Scrum Master) | manages the process for how information is exchanged. | 100000 | Hora | 35 | 3500000
IOT Devices | DHT11 | temperature and humidity sensor | 6500 | 1 | 1 | 6500 | not bought at market value
| nodeMCU | IOT device | 20000 | 1 | 1 | 20000 | not bought at market value
| photoresistance | luminity sensor | 4000 | 1 | 1 | 4000 | not bought at market value
| PCB | Printed Circuit Board | 28000 | 1 | 1 | 28000 | price subject to change
| shell | shell used to protect the device | 10000 | 1 | 1 | 10000 | price subject to change
backend
| lambda |  | 1000 | 1M requests | 1 | 1000
| EC2 |  | 20000 | Monhly750H | 1 | 20000
database |  |  | free
DynamoDB
frontend
| S3 |  | free
|  | Total | 9069500

## tiempos
Project Requirements
Category | Requirement | Effort (Hours) | Priority | Subdivision | Sprint No. | Comments
IoT Device | Sensor configuration | 7
| PCB Desing | 6
| PCB assambly | 4
| Box desing | 4
| Configuration Wizard UI | 8
| Configuration Wizard Core | 8
| Testing | 4
Backend | User Auth | 5
| DB Query | 3
| DB Update | 3
| REST API | 8
| Data Procesing | 6
| Testing | 3
DataBase | Data desing | 8
| Deploy | 3
Frontend | UX / UI desing | 4
| Component Construction | 12
| Backend Integration | 8
| Configutarion Tools | 4
| Dashboard dvelopment | 6
| Testing | 3
Architecture | Conceptual Model | 3
| Fisical Model | 3
| Technology comparassion | 2
| Deploy | 4
Planning and Managment | Weakly review | 7
| Task assignament | 14
| Reporting | 14
| Total | 164